# Minutes of the Working Group Meeting

# 08 December 2014, New Inn, Huby, 8 pm

Present:

Kathryn Wallis, Rachel Marshall, Terry Wolf (Chair), Paul Jackson, Roger Teare, Gary Dunning, Betty Tyson

- Apologies

Val Burnham.

- Declaration of interests

Rachel Marshall, Terry Wolf and Gary Dunning (Agenda Item 5 Site Assessment)

- Minutes of last meeting

The minutes of the meeting of 13/11/14 were accepted as a correct record.

- Matters arising (not elsewhere on agenda)

| Action | Status |
| --- | --- |
| Full budget update to be prepared for next meeting | Guy | Copy of budget breakdown given to group |
| Progress on consultation document and feedback form | Terry | Printed copies distributed to group |
| C/fwd: Green Space Designation for the three identified sites in village | Rachel to take this on |

- Process for commissioning the Independent review of the site assessment & historic assets study

TW has spoken to GR about the independent review of the site assessment process. GR said that the Parish Council would need to approve the tender specification and then three quotes would have to be sought. He questioned whether this was the best use of the available money and asked if there was another way to resolve this. TW consulted Mike Dando who suggested using some of the remaining Planning Aid time the group is entitled to for planning volunteers to scrutinise the document and sign off if acceptable. The group agreed that as long as someone with the expertise to sign off the document has done so they are happy for the full site assessment to be included in the final plan.

Action: Terry to chase Mike Dando for feedback

- Promotion activity

TW distributed copies of the printed consultation document. A decision was needed about whether to set up a freepost account or buy stamps for returning the completed feedback forms. After analysing the cost and time implications it was decided that TW would approach the Parish Clerk to have a Freepost account set up which could then be used by the Parish Council for the rest of the year’s subscription.

Although the group has missed the Huby Voice delivery deadline it was agreed that this was better as the Voice already carried a survey about the future of the village shop. The group agreed to hand deliver the documents during the Christmas break in order to give residents enough time to respond before the 26 January deadline.

The group agreed on 2 consultation dates in January – Saturday 10th between 10 and 12.30 at the Village Hall and Tuesday 21st between 7pm and 9pm at the Mended Drum.

The group discussed what the display would contain and agreed to Terry’s copy for new posters. It was agreed that the consultation displays should be as cost effective as possible and flipcharts with policy intentions could be used. The group will need to record names and addresses with feedback comments but this will be done in such a way as to protect the anonymity of the commenter.

TW noted that she would need to write to the site owners before the document is distributed and the consultation are held to inform them of what is included in the site assessment section.

Action: TW to book village hall. BT to speak to Mended Drum and buy refreshments for the 10th. TW to write to site owners. TW to send RM final poster copy for designer.

- AOB

TW reported that she has emailed the person at HDC who is representing Hambleton District Council  at the Public Inquiry next week about whether the Neighbourhood Plan team needed representation at the Inquiry. She has so far received no reply. The group agreed that at the very least a report should be prepared detailing work undertaken by the working party to date and any factual evidence that could be useful to the Inquiry. If a body is needed to respond during the Inquiry TW will attend on the 16th December.

Action: PJ to provide TW with a copy of the Housing Needs Survey results, TW to produce report for HDC.

- Date of next meeting: Monday 05/01/15  8 pm.  To finalise preparation for the consultation events. Venue tbc

Action points from Meeting 08/12/14

| Action | Who is to do | Timescale |
| --- | --- | --- |
| C/fwd: Green Space Designation for the three identified sites in village | Rachel | Asap |
| Chase Mike Dando for feedback and sign off of site assessment document | Terry | Asap |
| Book village hall for consultation event | Terry | Asap |
| Speak to Mended Drum re holding consultation event on 21st January | Betty | By 21/12/14 |
| Produce consultation posters | Terry to send Rachel poster text. Rachel to contact designer for printing | Asap |
| Write to site owners | Terry | Before document distribution |
| Send Terry copy of Housing Needs Survey results for report | Paul | Done |
| Produce report for HDC to use at Inquiry | Terry | Asap/Before 16/12/14 |
| Copy of the draft plan distributed to each household/business/other stakeholders in Huby together with a feedback questionnaire | Neighbourhood Plan team | By 03/01/15 |