Apologies: Val, Terry,

Minutes from meeting of 28/10/13 presented by Richard, minutes approved.

Matters

Project plan – end of March draft – Guy agreed to check with Mike Dando to extend beyond May

                Identify gaps in evidence

                Housing needs survey

Group Feedback:

7 groups replied, 4 more to reply

* Cricket Club 6/3/14 – Richard & Beki
* Methodist – Any Tuesday – Paul & Beki
* Huby Feast 21/1/14 8pm – Roger & Guy
* Karatee – Monday & Thursday – Richard
* Cubs – Richard
* Gardening 1/2/14 – Betty
* Bowls – TBC
* Sports & Social 23/1/14 – TBC (playing fields)
* Keepfit – Tuesday – kathryn

Area of discussion: Sports provision, Social provision, community use – guide sheet to be prepared for ensure that conversations are consistent

WI – Richard to chase e-mail

Plan writing – Paul to put into draft plan document (11/2/14) in the next few weeks then get in touch with Graham Banks for meeting – Guy, Beki, Val (policy writing)

Quick wins – spreadsheet from last meeting

* Kathryn – footpaths, needs assistance (advertise in March newsletter)
* Housing needs survey – HDC print, we send, return to HDC
* Newsletter to prepare and send
* Parish support plan for Huby NP to deal direct with HDC
* Landowners – put forward pieces of land for affordable housing
* Roger telephone update – article to be written for newsletter on phone reception
* Newsletter article – Tally Hill potential

Discussion of letter to landowners, decided not to write. Our position that we support policy and support affordable housing with no defined land allocation. If approached send enquiry to HDC

New Hall – RT to get file and copy – meeting with DH

Rachel – Quick wins group – agreed to meet and keep moving forward. Information need re village groups – suggested article for parish voice – publish names and list of groups on village notice board.

Happy to receive ongoing comments from parish residents

Meeting closed 9:15pm

Next meeting 18/2/14 – Paul to organise venue.